## AWS-1
MANAGEMENT UNIT NAME: Kenora Forest
PLAN PERIOD: 2022-2032
ANNUAL WORK SCHEDULE: 2025-2026
AWS - 1 ANNUAL SCHEDULE OF WATER CROSSINGS TO BE CONSTRUCTED/REVIEWED
Year of Construction | X | Y | Water Crossing Identifier | Road Identifier | Water Crossing Structure | Culvert Diameter (mm) 25yr flow | Water Crossing Standard Identifier | In Water Work Timing Restriction | Construction Conditions (25 yr flow) | Operational Management Zone (Y/N) | Future Removal (Y/N) | Fisheries Act Review Completed Previously (Y/N) | Fisheries Act Review Results
| 407893 | 5529320 | DEW-02 | Dewar Lake Road | CULV/BRDG | 2000 | CONST-CLR-BRDG | April 1st- June 20th |  | N | N | Y | Low
| 407992 | 5527394 | DEW-03 | Dewar Lake Road | CULV/BRDG | 1200 | CONST-CLR-BRDG CONST-SM-CULV | April 1st- June 20th |  | N | N | Y | Low
| 407192 | 5526710 | DEW-04 | Dewar Lake Road | CULV/BRDG | 1600 | CONST-CLR-BRDG | April 1st - July 15th |  | N | N | Y | Low
| 380825.5365 | 5528695.8783 | FLAPJ11.8 | Flapjack Road | CULV | 600 | CONST-SM-CULV | April 1st - July 15th |  | N | N | N | Low
| 381582.5638 | 5529056.4426 | FLAPJ12.6 | Flapjack Road | CULV | 1600 |  | April 1st - July 15th |  | N | N | N | Low
| 378812.3576 | 5527579.052 | FLAPJ9.1 | Flapjack Road | CULV | 2200 |  | April 1st - July 15th |  | N | N | N | Low
A. Current Year | 395509.8285 | 5552952.3753 | FLOR_03 | Flora Lake Road | CULV/BRDG | 800* | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 430286.1944 | 5446868.2812 | NAMGO-03 | Namego Lake Road | CULV/BRDG | 1400 | CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | Y | N | Y | Low
| 441599.2243 | 5456289.0291 | WEIS-01 | Weisner Lake Road | CULV/BRDG | 1400 | CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 441186.4734 | 5456263.629 | WEIS-02 | Weisner Lake Road | CULV/BRDG | 800 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 352852.3859 | 5473594.135 | WEIS-03 | Weisner Lake Road | CULV/BRDG | 1400 | CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 357616.1097 | 5477189.6189 | WP-04 | Westway Road | CULV/BRDG or ICE | 800 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 397756.2589 | 5539044.8582 | WP-05 | Westway Road | CULV/BRDG or ICE | 800* | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N | Y | Low
| 417397.2987 | 5476975.539 | X12.653-1 | 12.653 Road | CULV/BRDG or ICE | 900 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 444790.8216 | 5478332.935 | X22.001 | 22.027 Road | CULV/BRDG or ICE | 900 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 445466.7014 | 5478401.6666 | X22.002 | 22.028 Road | CULV/BRDG or ICE | 600 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 444449.1468 | 5460747.0164 | X22.003 | 22.044 Road | CULV/BRDG or ICE | 1200 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 441228.9129 | 5455757.8502 | X22.004 | 22.058 Road | BRDG/ICE | 1400 | CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 349663.9342 | 5525795.587 | X22.007 | 22.285 Road | CULV/BRDG or ICE | 800 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 382455.9194 | 5524536.73 | X22.008 | 22.349 Road | CULV/BRDG or ICE | 2000 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 374338.6175 | 5524589.8143 | X22.009 | 22.358 Road | CULV/BRDG or ICE | 1200 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 378177.6272 | 5522305.9274 | X22.010 | 22.364 Road | CULV/BRDG or ICE | 800 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 392612.1302 | 5550915.8323 | X22.018 | 22.539 Road | CULV/BRDG or ICE | 1000 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | Y | Y | Y | Low
| 441377.3707 | 5455855.6407 | X22.027 | 22.060 Road | CULV/BRDG or ICE | 1000 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 415383.279 | 5528010.5218 | X22.030 | K1997-1114 Road | CULV/BRDG or ICE | 1400 | CONST-CLR-BRDG CONST-ICE-SNOW | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 413697.078 | 5528335.68 | X22.031 | K1997-1114 Road | CULV/BRDG or ICE | 1200 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 445975.0405 | 5475949.2649 | X22.032 | 22.036 Road | CULV/BRDG or ICE | 1000 | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 445770.2509 | 5475614.8615 | X22.033 | 22.036 Road | CULV/BRDG or ICE | 600* | CONST-SM-CULV CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 350300.1401 | 5544668.2183 | X22.045 | 22.404 Road | CULV/BRDG or ICE | 1600 | CONST-ICE-SNOW CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 446598 | 5476090 | X22.048 | 22.010 Road | CULV/BRDG or ICE | 500 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 394741.4879 | 5552725.8637 | X23.001 | Namego Lake Road | CULV/BRDG or ICE | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | Y | Y | Y | Low
| 391905.9423 | 5551744.7504 | X23.002 | India Road | CULV/BRDG | 1200 | CONST-CLR-BRDG CONST-SM-CULV | September 1st - May 31st |  | Y | Y | Y | Low
| 391612.2542 | 5551943.1883 | X23.003 | India Road | CULV/BRDG | 1200 | CONST-CLR-BRDG CONST-SM-CULV | September 1st - May 31st |  | Y | Y | Y | Low
| 391040.753 | 5552078.126 | X23.004 | India Road | CULV/BRDG | 800 | CONST-CLR-BRDG CONST-SM-CULV | September 1st - May 31st |  | Y | Y | Y | Low
| 388774.3718 | 5552041.0843 | X23.005 | 22.552 Road | CULV/BRDG or ICE | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | Y | Y | Y | Low
| 388536.2463 | 5552130.3813 | X23.006 | Roxy Road | CULV/BRDG or ICE | 1200 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | Y | Y | Y | Low
| 382618.3629 | 5524779.6268 | X23.010 | 22.349 Road | CULV/BRDG or ICE | 2000 | CONST-CLR-BRDG CONST-ICE-SNOW | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 415753.3513 | 5478870.9502 | X23.014 | 22.191 Road | CULV/BRDG or ICE | 500 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | Low
| 442162.7844 | 5456893.333 | X23.015 | 22.061 Road | CULV/BRDG or ICE | 900 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 350266 | 5523529 | X23.029 | 22.288 Road | CULV | 1000 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 350105 | 5523139 | X23.030 | 22.288 Road | CULV | 1200 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | Y | Low
| 351528.6974 | 5520359.7554 | X23.031 | 22.283 Road | CULV | 1600 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N | Low
| 357145.0293 | 5542099.922 | X24.001 | 22.397 Road | CULV | 900 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | Low
| 351876.5638 | 5543715.3167 | X24.002 | 22.403 Road | CULV | 1200 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | Low
| 388755.9035 | 5551703.4242 | X24.003 | 22.552 Road | CULV | 1400 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N | Low
| 351902.6862 | 5530726.8529 | X24.004 | 22.305 Road | CULV | 900 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | Low
| 380146.2459 | 5521575.0085 | X24.005 | 22.363 Road | CULV | 1000 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | Low
| 398258 | 5553514 | X24.006 | 22.563 Road | BRDG | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | Y | Y | N/A | Low
| 383669 | 5540338 | X24.009 | 22.523 Road | CULV | 1800 | CONST-CLR-BRDG CONST-ICE-SNOW | April 1st- June 20th |  | N | Y |  | LOW
| 353077 | 5543541 | X24.010 | 22.400 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | NA
| 350132 | 5530048 | X24.011 | 22.304 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | NA
| 352145 | 5531467 | X24.012 | 22.306 Road | CULV | 500 | CONST-SM_CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | NA
| 351933 | 5532021 | X24.013 | 22.306 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y | N/A | NA
| 351933.9814 | 5532021.6538 | X25.001 | 22.306 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 349126.7937 | 5529521.2816 | X25.002 | Atik Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | N |  | NA
| 348520.4381 | 5530115.14 | X25.003 | Atik Road | CULV | 3050 (100yr) | CONST-CLR-BRDG | April 1st- June 20th |  | N | N |  | LOW
| 347839.7035 | 5531320.8884 | X25.004 | Atik Road | CULV | 1600 (100yr) | CONST-CLR-BRDG | April 1st- June 20th | Ice - remove by Mar 15. | N | N |  | LOW
| 354572.2517 | 5549133.2292 | X25.008 | 22.407 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 356150.9972 | 5549446.4083 | X25.009 | 22.407 Road | CULV | 1200 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 356455.2686 | 5550240.1489 | X25.010 | 22.408 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 352047.1529 | 5529384.0253 | X25.011 | 22.310 Road | CULV | 1400 | CONST-CLR-BRDG CONST-ICE-SNOW | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | LOW
| 351202.1673 | 5529469.0467 | X25.012 | 22.311 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 378609.5543 | 5523641.3787 | X25.014 | 22.362 Road | CULV | 600 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 374911.5869 | 5522646.7088 | X25.015 | 22.359 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 353888.2562 | 5548180.4627 | X25.006 | 22.406 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 353725.3827 | 5548673.1399 | X25.005 | 22.406 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
| 352823.4715 | 5549305.2087 | X25.007 | 22.405 Road | CULV | 800 | CONST-CLR-BRDG CONST-ICE-SNOW CONST-SM-CULV | April 1st- June 20th | Ice - remove by Mar 15. | N | Y |  | NA
B. Future Year

## AWS-2
MANAGEMENT UNIT NAME: Kenora Forest
PLAN PERIOD: 2022-2032
ANNUAL WORK SCHEDULE: 2025-2026
AWS - 2 ANNUAL SCHEDULE OF WATER CROSSINGS TO BE DECOMMISSIONED
Water Crossing Identifier | X | Y | Road Identifier | Water Crossing Structure | Water Crossing Standard Identifier | Decommissioning Activities/Conditions | Fisheries Act Review Completed | Fisheries Act Review Results
WHIF8.2 | 350746 | 5517264 | Whitefish Road | CULV | DECOM-SM-CULV | Removal of 1000mm Culvert
WHIF6.18 | 351930 | 5518613 | Whitefish Road | BRDG | DECOM-CLR-BRDG | Removal of Bridge - 20'
WHIF1.24 | 354011 | 5521343 | Whitefish Road | BRDG | DECOM-CLR-BRDG | Removal of Bridge - 30'
X12.013-1 | 401615 | 5541304 | 12.013 Road | BRDG | DECOM-CLR-BRDG | Removal of Bridge - 16'
X12.125-4 | 376482 | 5553323 | 12.125 Road | BRDG | DECOM-CLR-BRDG | Removal of Bridge - 30'
X22.014 | 402463 | 5540987 | 22.512 Road | BRDG | DECOM-CLR-BRDG | Removal of Bridge - 16'